## Daily Gantt Chart
DAILY GANTT CHART – 30-DAY PROJECT TIMELINE
Project: Product Launch Campaign
Timeline start date: | 2026-11-02
Task | Assigned To | Start | Days | End
Define launch goals & KPIs | Marketing Mgr |  | 3
Audience research | Analyst |  | 4
Messaging & positioning | Copywriter |  | 4
Landing page copy | Copywriter |  | 4
Landing page design | Designer |  | 5
Email sequence (3 emails) | Email Specialist |  | 5
Social media content | Social Lead |  | 7
Paid ads setup | Ads Specialist |  | 4
Press kit & outreach | PR Lead |  | 6
Final review & approvals | Marketing Mgr |  | 3
Launch day | Team |  | 1
Post-launch report | Analyst |  | 4
Total task-days scheduled:
Grey columns = weekends. Red = one-day milestone. Change the start date and every date shifts.