## Gantt with Milestones
GANTT CHART WITH MILESTONES & PHASES
Project: Office Relocation
Start week (Mon): |  | 2026-11-02
WBS | Phase / Task / Milestone | Start | Days | Type | End | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1 | Phase 1: Planning |  |  | Phase
1.1 | Define space requirements |  | 5 | Task |  | Complete
1.2 | Shortlist and visit sites |  | 10 | Task |  | Complete
1.3 | ◆ Lease signed |  | 0 | Milestone |  | Complete
2 | Phase 2: Preparation |  |  | Phase
2.1 | Office layout & furniture order |  | 12 | Task |  | In Progress
2.2 | IT & network setup |  | 14 | Task |  | In Progress
2.3 | Staff communication plan |  | 6 | Task |  | Not Started
2.4 | ◆ Fit-out complete |  | 0 | Milestone |  | Not Started
3 | Phase 3: Move |  |  | Phase
3.1 | Pack and label |  | 7 | Task |  | Not Started
3.2 | Moving day |  | 2 | Task |  | Not Started
3.3 | Unpack & test systems |  | 5 | Task |  | Not Started
3.4 | ◆ Office open |  | 0 | Milestone |  | Not Started
4 | Phase 4: Close-out |  |  | Phase
4.1 | Snag list and final payments |  | 10 | Task |  | Not Started
4.2 | ◆ Project review |  | 0 | Milestone |  | Not Started
| Milestones: |  | Done:
Dark purple = phase span · green = completed task · ◆ = milestone. Phase dates roll up from their tasks.