## Party Countdown
PARTY PLANNING COUNTDOWN CHECKLIST
Party: | Ava's 10th Birthday Party |  | Party date: | 2026-12-12
Guests: | 25 |  | Budget: | 750
Done | Task | Owner | Due Date | Est. Cost | Actual Cost | Notes
6 WEEKS BEFORE
Yes | Set the date, time and budget | Mom |  | 0 | 0
Yes | Choose a theme | Ava |  | 0 | 0
Yes | Book venue or plan home setup | Dad |  | 150 | 150
4 WEEKS BEFORE
Yes | Make the guest list | Mom |  | 0 | 0
Yes | Send invitations and track RSVPs | Mom |  | 25 | 22
| Book entertainment | Dad |  | 120 | 120
2 WEEKS BEFORE
| Plan the menu and order the cake | Mom |  | 140
| Buy decorations and tableware | Aunt Sara |  | 60
| Prepare games and party favors | Ava |  | 45
1 WEEK BEFORE
| Confirm final guest count | Mom |  | 0
| Confirm vendors and delivery times | Dad |  | 0
| Create a setup timeline | Mom |  | 0
DAY BEFORE
| Shop for fresh food and drinks | Dad |  | 60
| Decorate and set up tables | Everyone |  | 0
PARTY DAY
| Pick up the cake | Dad |  | 0
| Set out food, drinks and music | Everyone |  | 0
| Clean up and send thank-you notes | Mom |  | 0
TOTALS
| Tasks done |  |  | Type Yes in the Done column to tick a task.
| Progress |  |  | Due dates count back from the party date.
Days to go
Budget left (estimate)