## Project Gantt Chart
PROJECT GANTT CHART
Project: | Website Redesign |  |  | Manager: | [Name]
Project Start (Monday): | 2026-11-02 |  |  | Overall %:
Task | Owner | Start | End | Days | % Done | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1. Planning
Kick-off meeting | Project Mgr |  |  | 2 | 100%
Requirements gathering | Analyst |  |  | 8 | 100%
Sitemap & content plan | Content Lead |  |  | 7 | 100%
2. Design
Wireframes | UX Designer |  |  | 10 | 100%
Visual design mockups | UI Designer |  |  | 12 | 80%
Design review & sign-off | Client |  |  | 4 | 25%
3. Development
Front-end build | Developer |  |  | 20 | 0%
CMS integration | Developer |  |  | 15 | 0%
Content migration | Content Lead |  |  | 12 | 0%
4. Launch
Testing & QA | QA Tester |  |  | 10 | 0%
Training | Project Mgr |  |  | 4 | 0%
Go live | Team |  |  | 2 | 0%
Legend: |  | Completed |  | Remaining
Enter a start offset, duration and % done; End date, bars and progress update automatically.