## Project Plan
PROJECT PLAN WITH TIMELINE
Project: | Website Redesign |  |  | Plan Start: |  | 2026-11-02
Manager: | J. Patel |  |  | Target Finish: |  | 2027-01-22
ID | Phase / Task | Owner | Start | End | Days | Status | % Done
1 | INITIATION
1.1 | Define goals and success measures | J. Patel | 2026-11-02 | 2026-11-06 |  | Complete | 100%
1.2 | Stakeholder kickoff meeting | J. Patel | 2026-11-09 | 2026-11-10 |  | Complete | 100%
2 | PLANNING
2.1 | Site audit and content inventory | A. Gomez | 2026-11-09 | 2026-11-20 |  | Complete | 100%
2.2 | Sitemap and wireframes | L. Chen | 2026-11-16 | 2026-11-27 |  | In Progress | 60%
2.3 | Budget and resource plan | J. Patel | 2026-11-23 | 2026-11-27 |  | In Progress | 50%
3 | EXECUTION
3.1 | Visual design mockups | L. Chen | 2026-11-30 | 2026-12-11 |  | Not Started | 0%
3.2 | Front-end development | R. Okafor | 2026-12-07 | 2027-01-01 |  | Not Started | 0%
3.3 | Content migration | A. Gomez | 2026-12-14 | 2027-01-08 |  | Not Started | 0%
3.4 | Testing and fixes | R. Okafor | 2027-01-04 | 2027-01-15 |  | Not Started | 0%
4 | CLOSING
4.1 | Launch and handover | J. Patel | 2027-01-18 | 2027-01-20 |  | Not Started | 0%
4.2 | Post-launch review | J. Patel | 2027-01-21 | 2027-01-22 |  | Not Started | 0%
PROJECT SUMMARY
Tasks |  |  |  | Blue bars = scheduled weeks, green = completed tasks. Red end date = overdue.
Complete |  |  |  | Change the plan start date (G2) to move the weekly timeline.
In progress
Overall progress
Overdue tasks