## Work Order Tracker
WORK ORDER TRACKER / LOG
[8 empty] | Report date: |  |  |  | 2026-11-10
(type a date, or enter =TODAY())
WO # | Opened | Requested By | Location | Description | Priority | Assigned To | Status | Due Date | Closed | Days Open | Overdue?
WO-3101 | 2026-10-25 | Facilities | Warehouse dock 2 | Repair dock leveler hydraulic leak | High | R. Diaz | Completed | 2026-10-29 | 2026-10-28
WO-3102 | 2026-10-27 | Office Mgr | Floor 3 kitchen | Replace leaking faucet cartridge | Low | J. Ortiz | Completed | 2026-11-03 | 2026-11-01
WO-3103 | 2026-10-29 | IT Dept | Server room | Install additional cooling vent | Medium | M. Fischer | In Progress | 2026-11-13
WO-3104 | 2026-10-30 | Security | Parking lot B | Replace two failed light poles | High | Ace Electric | On Hold | 2026-11-08
WO-3105 | 2026-11-01 | Reception | Main lobby | Fix automatic door sensor | Urgent | R. Diaz | Completed | 2026-11-02 | 2026-11-02
WO-3106 | 2026-11-03 | HR | Training room | Mount 75" display and cabling | Low | AV Team | Scheduled | 2026-11-20
WO-3107 | 2026-11-04 | Harbor View | Building C lobby | Ceiling tiles and drywall repair | Medium | J. Ortiz | In Progress | 2026-11-11
WO-3108 | 2026-11-06 | Production | Line 2 | Replace conveyor belt motor | Urgent | M. Fischer | Open | 2026-11-09
WO-3109 | 2026-11-08 | Finance | Floor 2 | Repaint meeting room walls | Low | Paint Crew | Open | 2026-11-30
SUMMARY |  |  | KEY METRICS
Open |  |  | Total work orders
Scheduled |  |  | Overdue
In Progress |  |  | Avg. days to close
On Hold |  |  | Completion rate
Completed